## Milestones
Milestone | Milestone Description | Estimated Days
Project Research | Task, Objective and Plan of actions
Run a feasibility test on one the categories to test the access and security measure bypass on the salesforce appexchange site | Use selenium to create a sample code of py script to visit Salesforce appexchange site and click checkboxes under "Business Need" Tab to verify accessibility for selenium tool. | 2
Once feasibility suceceeds
Milestone 1 : Begin selenium based py script development to scrape data of "Business Need" Tab
1) Fetch entire Company List | Refer the process to fetch the list of companies from salesforce data collection document under Section 1 : - Point 1 to 3 | 1
2) Extract data from each company | Refer to the Section 2 of the document for scrapping the data from 3 different sections for each company
| a) Overview | 3
| b) Review | 3
| c) More Details | 2
3) Format the extracted data | Storeand format the extracted data from Dataframes to the required format of tables in text file/excel file | 2
Milestone 2 : Begin selenium based py script development to scrape data of "Products" Tab
1) Fetch entire Company List | Refer the process to fetch the list of companies from salesforce data collection document under Section 1 : - Point 4 to 6 | 1
2) Extract data from each company | Refer to the Section 2 of the document for scrapping the data from 3 different sections for each company
| a) Overview | 2
| b) Review | 2
| c) More Details | 2
3) Format the extracted data | Storeand format the extracted data from Dataframes to the required format of tables in text file/excel file | 2
Milestone 3 : Begin selenium based py script development to scrape data of "Industries" Tab
1) Fetch entire Company List | Refer the process to fetch the list of companies from salesforce data collection document under Section 1 : - Point 7 to 8 | 1
2) Extract data from each company | Refer to the Section 2 of the document for scrapping the data from 3 different sections for each company
| a) Overview | 1
| b) Review | 1
| c) More Details | 2
3) Format the extracted data | Storeand format the extracted data from Dataframes to the required format of tables in text file/excel file | 1
Milestone 4 : Begin selenium based py script development to scrape data of "Salesforce Labs" Tab
1) Fetch entire Company List | Refer the process to fetch the list of companies from salesforce data collection document under Section 1 : - Point 9 - 10 | 1
2) Extract data from each company | Refer to the Section 2 of the document for scrapping the data from 3 different sections for each company
| a) Overview | 1
| b) Review | 1
| c) More Details | 2
3) Format the extracted data | Storeand format the extracted data from Dataframes to the required format of tables in text file/excel file | 1
Milestone 5 : Begin selenium based py script development to scrape data of "Impact" Tab
1) Fetch entire Company List | Refer the process to fetch the list of companies from salesforce data collection document under Section 1 : - Between Point 10 and 11 | 1
2) Extract data from each company | Refer to the Section 2 of the document for scrapping the data from 3 different sections for each company
| a) Overview | 1
| b) Review | 1
| c) More Details | 2
3) Format the extracted data | Storeand format the extracted data from Dataframes to the required format of tables in text file/excel file | 1
Milestone 6 : Begin selenium based py script development to scrape data of "Business Need" Tab, but with a search string of "Agentforce"
1) Fetch entire Company List | Within the search bar type “agentforce.” This should yield a list of (roughly, as of when this doc was created on Jan 8, 2025) 28 apps. Refer the document salesforce data collection document under Section 1 : - Point 11 | 1
2) Extract data from each company | Refer to the Section 2 of the document for scrapping the data from 3 different sections for each company
| a) Overview | 1
| b) Review | 1
| c) More Details | 2
3) Format the extracted data | Storeand format the extracted data from Dataframes to the required format of tables in text file/excel file | 1
Milestone 7 : Combine all the Tab Scrappers into one and test the entire script once for data fetch without errors, add error handling and exception handlings code snippets to avoid scrapping breakage. | Combining, Final Test and Review | 4
Milestone 8: | update data on monthly basis | By 3rd of every month should be good. It will include updates of entire prev month.