## Milestones
Date Created | Who | Milestone | Milestone Description | Estimated Days | Approval | Actual Days Spent | %Completion | Deliverable | Loom Links (Updates)
2025-01-21 | Blackcoffer | Project Research | Task, Objective and Plan of actions
2025-01-21 | Blackcoffer | Run a feasibility test on one the categories to test the access and security measure bypass on the salesforce appexchange site | Use selenium to create a sample code of py script to visit Salesforce appexchange site and click checkboxes under "Business Need" Tab to verify accessibility for selenium tool. | 2 | Yes |  | 100% | Excel output file
Once feasibility suceceeds
2025-01-21 | Blackcoffer | Milestone 1 : Begin selenium based py script development to scrape data of "Business Need" Tab
|  | 1) Fetch entire Company List | Refer the process to fetch the list of companies from salesforce data collection document under Section 1 : - Point 1 to 3 | 1 | Yes |  | 96.09% | Fetch 4,993 results as per possible request to server response Link | Date : 27/01/2025 Loom - https://www.loom.com/share/b40c07a4e9da44a3a149eace13086a33?sid=71d42547-8cc4-446a-9447-abb3fe24fade
|  | 2) Extract data from each company | Refer to the Section 2 of the document for scrapping the data from 3 different sections for each company
|  |  | a) Overview | 3 | Yes |  | 100% | Extracted data of company profile summary, info and overview Here is preview data of 100 rows extraction- Link
|  |  | i) Profile summary | 1 | Yes |  | 100% | Extracted Profile name, company name, ratings , review section and company description
|  |  | ii) Profile Info | 1 | Yes |  | 100% | Extracted Pricing details along with Industries, Business needs, Requires and Compatible with section information
|  |  | iii) ads-grid-item | 2 | Yes |  | 100% | Extracted provider details and contact details with company description
|  |  | b) Review | 3 | Yes |  | 100% | Successfully navigated to review section of each link and able to click "Show More" button and Extracted Reviewer name, valence, Likes, Date & Text along with Badges count Here is the preview of extracted data - Link
|  |  | i) Reviewer name, valence & likes |  |  |  | 100%
|  |  | ii) Review Date & Review Text |  |  |  | 100%
|  |  | iii) MVP, Ranger & Top Review Badges |  |  |  | 100%
|  |  | c) More Details | 2 | Yes |  | 100% | Extract Data of Compatibility, App Details, Contents & Components Here is preview data of 100 rows extraction- Link
|  |  | i) Compatibility section |  |  |  | 100%
|  |  | ii) App Details |  |  |  | 100%
|  |  | iii) Contents & Components |  |  |  | 100%
|  | 3) Format the extracted data | Storeand format the extracted data from Dataframes to the required format of tables in text file/excel file | 2 | Yes |  | 100% | Extracted - Data and Reviews
2025-01-21 | Blackcoffer | Milestone 2 : Begin selenium based py script development to scrape data of "Products" Tab
|  | 1) Fetch entire Company List | Refer the process to fetch the list of companies from salesforce data collection document under Section 1 : - Point 4 to 6 | 1 | Yes |  | 100% | Successfully extracted all results of all radio button clicks and filters Link
|  | 2) Extract data from each company | Refer to the Section 2 of the document for scrapping the data from 3 different sections for each company
|  |  | a) Overview | 2 | Yes |  | 100% | Extracted data of company profile summary, info and overview Here is preview data of 100 rows extraction- Link
|  |  | b) Review | 2 | Yes |  | 100% | Successfully navigated to review section of each link and able to click "Show More" button and Extracted Reviewer name, valence, Likes, Date & Text along with Badges count Here is the preview of extracted data - Link
|  |  | c) More Details | 2 | Yes |  | 100% | Extract Data of Compatibility, App Details, Contents & Components Here is preview data of 100 rows extraction- Link
|  | 3) Format the extracted data | Storeand format the extracted data from Dataframes to the required format of tables in text file/excel file | 2 | Yes |  | 100% | Extracted - Data and Reviews
2025-01-21 | Blackcoffer | Milestone 3 : Begin selenium based py script development to scrape data of "Industries" Tab
|  | 1) Fetch entire Company List | Refer the process to fetch the list of companies from salesforce data collection document under Section 1 : - Point 7 to 8 | 1 | Yes |  | 100% | Successfully extracted all 2458 results Link
|  | 2) Extract data from each company | Refer to the Section 2 of the document for scrapping the data from 3 different sections for each company
|  |  | a) Overview | 1 | Yes |  | 100% | Extracted data of company profile summary, info and overview Here is preview data of 100 rows extraction- Link
|  |  | b) Review | 1 | Yes |  | 100% | Successfully navigated to review section of each link and able to click "Show More" button and Extracted Reviewer name, valence, Likes, Date & Text along with Badges count Here is the preview of extracted data - Link
|  |  | c) More Details | 2 | Yes |  | 100% | Extract Data of Compatibility, App Details, Contents & Components Here is preview data of 100 rows extraction- Link
|  | 3) Format the extracted data | Storeand format the extracted data from Dataframes to the required format of tables in text file/excel file | 1 | Yes |  | 100% | Extracted - Data and Reviews
2025-01-21 | Blackcoffer | Milestone 4 : Begin selenium based py script development to scrape data of "Salesforce Labs" Tab
|  | 1) Fetch entire Company List | Refer the process to fetch the list of companies from salesforce data collection document under Section 1 : - Point 9 - 10 | 1 | Yes |  | 100% | Successfully extracted all 583 results Link
|  | 2) Extract data from each company | Refer to the Section 2 of the document for scrapping the data from 3 different sections for each company
|  |  | a) Overview | 1 | Yes |  | 100% | Extracted data of company profile summary, info and overview Here is preview data of 100 rows extraction- Link
|  |  | b) Review | 1 | Yes |  | 100% | Successfully navigated to review section of each link and able to click "Show More" button and Extracted Reviewer name, valence, Likes, Date & Text along with Badges count Here is the preview of extracted data - Link
|  |  | c) More Details | 2 | Yes |  | 100% | Extract Data of Compatibility, App Details, Contents & Components Here is preview data of 100 rows extraction- Link
|  | 3) Format the extracted data | Storeand format the extracted data from Dataframes to the required format of tables in text file/excel file | 1 | Yes |  | 100% | Extracted - Data and Reviews
2025-01-21 | Blackcoffer | Milestone 5 : Begin selenium based py script development to scrape data of "Impact" Tab
|  | 1) Fetch entire Company List | Refer the process to fetch the list of companies from salesforce data collection document under Section 1 : - Between Point 10 and 11 | 1 | Yes |  | 100% | Successfully extracted all 990 results Link
|  | 2) Extract data from each company | Refer to the Section 2 of the document for scrapping the data from 3 different sections for each company
|  |  | a) Overview | 1 | Yes |  | 100% | Extracted data of company profile summary, info and overview Here is preview data of 100 rows extraction- Link
|  |  | b) Review | 1 | Yes |  | 100% | Successfully navigated to review section of each link and able to click "Show More" button and Extracted Reviewer name, valence, Likes, Date & Text along with Badges count Here is the preview of extracted data - Link
|  |  | c) More Details | 2 | Yes |  | 100% | Extract Data of Compatibility, App Details, Contents & Components Here is preview data of 100 rows extraction- Link
|  | 3) Format the extracted data | Storeand format the extracted data from Dataframes to the required format of tables in text file/excel file | 1 | Yes |  | 100% | Extracted - Data and Reviews
2025-01-21 | Blackcoffer | Milestone 6 : Begin selenium based py script development to scrape data of "Business Need" Tab, but with a search string of "Agentforce"
|  | 1) Fetch entire Company List | Within the search bar type “agentforce.” This should yield a list of (roughly, as of when this doc was created on Jan 8, 2025) 28 apps. Refer the document salesforce data collection document under Section 1 : - Point 11 | 1 | Yes |  | 100% | Successfully extracted all available results under "Agentforce" search term Link
|  | 2) Extract data from each company | Refer to the Section 2 of the document for scrapping the data from 3 different sections for each company
|  |  | a) Overview | 1 | Yes |  | 100% | Extracted data of company profile summary, info and overview Here is preview data of 100 rows extraction- Link
|  |  | b) Review | 1 | Yes |  | 100% | Successfully navigated to review section of each link and able to click "Show More" button and Extracted Reviewer name, valence, Likes, Date & Text along with Badges count Here is the preview of extracted data - Link
|  |  | c) More Details | 2 | Yes |  | 100% | Extract Data of Compatibility, App Details, Contents & Components Here is preview data of 100 rows extraction- Link
|  | 3) Format the extracted data | Storeand format the extracted data from Dataframes to the required format of tables in text file/excel file | 1 | Yes |  | 100% | Extracted - Data and Reviews
2025-01-21 | Blackcoffer | Milestone 7 : Combine all the Tab Scrappers into one and test the entire script once for data fetch without errors, add error handling and exception handlings code snippets to avoid scrapping breakage. | Combining, Final Test and Review | 4 | Yes |  | 100% | Extracted - Data and Reviews
2025-01-21 | Blackcoffer | Milestone 8: | Data Scrapping to be done and result to be provided by 3rd of every month. Result will include data of prev month. | 6 | Yes |  |  | Feb 2025 March 2025 April 2025 May 2025 June 2025
2025-05-08 | Blackcoffer | Maintenance Work of Selenium script Maintaining properly the selenium data extraction script with up-to-date changes in web elements, tags, nodes etc and keep monitoring recent changes in the website structure for extracting following things:
|  | 1) List of App names along with link and unique ID 2) Metadata extraction of each app from list 3) Extracting reviews of each app from list | 1) Modifying and updating list of App names along with link and unique ID selenium script to navigate appropriate web elements | 1 |  | 1 | 100% | Updated App list selenium script on Github
|  |  | 2) Modifying and Updating the metadata extraction code with changing in the tag elements and addition/removal of slot and nested shadow root element | 1 |  | 1 | 100% | Updated metadata extraction selenium script. Here is the github link - The script
2025-06-03 | Blackcoffer | Updating Selenium script Updating the Selenium data extraction script to incorporate the latest changes in web elements, tags, nodes, and overall website structure.
|  | 1) Updating the top profile section of each app | 1) Updating the reviews and ratings codeblock | 1 |  | 1 | 100% | Updated Reviews and Ratings extraction wth error handling Github - Link
|  |  | 2) Updating the Overview section variable to Navigate link of More Details | 1 |  | 1 | 100% | Updated More Details and overview section code block
|  |  | 3) Updating the Show More click button .onetrust cookie banner overlay handling | 1 |  | 1 | 100% | Added cookie banner overlay removal for clicking button
|  | 2) Updating reviews extraction selenium script | Update review extraction script to extract valence and date | 1 |  | 1 | 100% | Updated review extraction script Github - Link
|  | 3) Resolving wds-button error handling | Add wds-button tag element error handling if not present then it should do extraction process | 1 |  | 1 | 100% | Added missing tag elements error handling Github - Link

## Deliverables
Deliverable Compotents | Required? | Deliverable Reference
Solution Architecture | Yes
Project Documentation | Yes
Data Science Source code | Yes
Frontend Source code | x
Backend Source code | x
Product Design | x
Product Database | x
Project Web App | x
Product android App | x
Product iOS App | x
Product Server | x
Software 1 | x
Software 2 | x
Software 3 | x
Software Tool 1 | x
Software Tool 2 | x
Software Tool 3 | x